## Sheet1
AGILE SPRINT BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE HOURS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #2 As a user, I want to access the service using phone and desktop so that I can use it on the go. | 3 |  | Completed
Create the app so that it can be displayed in the browser | 3 | All |  | 3 | 2 | 1 | 0 | 0 | 0
User Story #4 As an athlete, I want to see a heatmap for the front and back of my body so that I can get a good overview. | 5 |  | Completed
Display model on screen | 1.5 | Fergus |  | 8 | 8 | 4 | 2 | 2 | 0
Create models for all muscles | 1 | Fergus |  | 7 | 7 | 7 | 7 | 1 | 0
Add, modify controls | 1 | Fergus |  | 2 | 2 | 2 | 0 | 0 | 0
Colour models | 0.5 | Fergus |  | 4 | 4 | 4 | 4 | 0 | 0
Provide interface for real time update | 1 | Fergus |  | 3 | 3 | 3 | 3 | 0 | 0
User story #6 As an athlete, I want to view a live heatmap of my workout so that I can see how engaged my muscles are. | 13 |  | Completed
Read in data from single CSV | 0.5 | Mikolaj |  | 1 | 1 | 0 | 0 | 0 | 0
Change data into an appropriate format | 2 | Mikolaj |  | 2 | 3 | 2 | 0 | 0 | 0
Store the data from each file in a DataFrame array, then change it to a dict | 0.5 | Mikolaj |  | 2 | 1 | 1 | 1 | 1 | 0
Change data to JS | 3 | Mikolaj |  | 3 | 0 | 0 | 0 | 0 | 0
Provide buffer for recieving data | 2 | Scott, Mikolaj |  | 3 | 3 | 3 | 2 | 1 | 0
Extend for multiple sensors | 5 | Scott, Mikolaj |  | 10 | 10 | 10 | 10 | 6 | 0
User Story #36 As a user, I want to have a secure login so that I can keep my data protected. | 5 |  | Completed
Create login form | 2 | Bjarne, Alina |  | 5 | 3 | 2 | 2 | 2 | 0
provide option to logout | 1 | Bjarne |  | 1 | 2 | 2 | 2 | 1 | 0
Display info according to permissions | 2 | Bjarne |  | 6 | 3 | 3 | 2 | 0 | 0
User Story #33 As a therapist, I want to easily view my clients’ heatmap so that I can review the data. | 2 |  | Completed
Display heatmap in athlete view for therapist | 2 | Alina |  | 5 | 3 | 2 | 2 | 1 | 0
User Story #9 As a therapist, I want to add a new client so that I can have multiple clients. | 3 |  | Completed
Create form for adding new athlete user | 2 | Alina |  | 10 | 10 | 8 | 6 | 2 | 0
Show personal info on athlete page | 1 | Alina |  | 4 | 4 | 4 | 4 | 2 | 0
User Story #40 As a therapist, I want to see a list of all my clients so that I can monitor numbers. | 1 |  | Completed
Show list of clients | 1 | Bjarne, Alina |  | 3 | 1 | 1 | 0 | 0 | 0
User Story #7 As a user, I want to see the companies branding so that I can identify the websites origin. | 2 |  | Completed
Find information about colours, fonts, images, styleing | 1 | Alina |  | 1 | 0 | 0 | 0 | 0 | 0
Apply styling | 1 | Alina |  | 3 | 3 | 2 | 2 | 0 | 0
User Story #1 As a user, I want the product to be user friendly so that I can use it easily. | 3 |  | Completed
research user friendly design | 1 | All |  | 2 | 0 | 0 | 0 | 0 | 0
implementation | 2 | Alina |  | 3 | 3 | 2 | 0 | 0 | 0
User Story #28 As a user, I want to have an aesthetically pleasing application so that I can be inspired to use it. | 3 |  | Completed
research design from client page | 1 | Alina, Godfrey |  | 1 | 0 | 0 | 0 | 0 | 0
implement bootstrap/css for layout | 2 | Alina |  | 4 | 4 | 3 | 3 | 1 | 0
User Story #18 As a user, I want to set the colour scheme to account for color blindness so that I can use the app with my disability. | 2 |  | Completed
research colour scheme | 1 | Alina |  | 1 | 0 | 0 | 0 | 0 | 0
implement css code | 1 | Alina |  | 1 | 1 | 1 | 0 | 0 | 0
Testing | 3 | All | Completed | 8 | 7 | 5 | 3 | 2 | 0
Create a website header, footer | 1 | Alina | Completed | 2 | 2 | 2 | 0 | 0 | 0
Hosting on Azure | 3 | Patrizio, Alan | Completed | 7 | 6 | 4 | 3 | 2 | 0
TOTAL ACTUAL | 49 |  |  | 115 | 96 | 78 | 58 | 24 | 0
ESTIMATED |  |  |  | 115 | 92 | 69 | 46 | 23 | 0
Status
[11 empty] | Not started | 0
[11 empty] | In progress | 0
[11 empty] | To test | 0
[11 empty] | Completed | 12

## Sheet2
Sprint Backlog 1
BACKLOG TASK & ID | STORY POINTS | STATUS | ORIGINAL ESTIMATE HOURS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a user, I want to generate PANGU format crater and boulder lists #11 | 5 | On Going | 8
Print out txt files in a PANGU list format | 1 |  | 2 | 2 | 0 | 0 | 0 | 0
keep the list inforamtion in a datat structure | 2 |  | 3 | 2 | 0 | 0 | 0 | 0
be able to print both a crater and boulder list when both have been placed | 1.5 |  | 2 | 2
include all nessisary information(size,age,depth) | 0.5 |  | 1 | 1
As a user, I want to be able to specify where on the model I want to place Boulders or craters#2 | 5 | On Going | 6
Pick a Point on a model with the mouse (x,y,z) | 2 |  | 2.5 | 2.5 | 0 | 0 | 0 | 0
Convert that x,y,z position to longitude and latatude for PANGU | 2 |  | 2.5 | 2.5 | 2 | 0 | 0 | 0
Save the point so it can be added to the lists | 1 |  | 1 | 1 | 1 | 1 | 0 | 0
As a user, I want to swap between adding boulders or craters #5 | 5 | Done | 5
Add boulder and crater modes that can be toggled between | 1.5 |  | 2 | 2 | 0 | 0 | 0 | 0
add a UI element on the designer the user can use to pick which mode they want to use | 2.5 |  | 2 | 2 | 2 | 0 | 0 | 0
save boulders and craters to different strings | 1 |  | 1 | 1 | 0 | 0 | 0 | 0
As a user, I want to be able to access the service through a web-site #8 | 2 | Done | 2
Create a html page | 1 |  | 1 | 1 | 0 | 0 | 0 | 0
locally host the page | 1 |  | 1 | 1 | 0 | 0 | 0 | 0