## Sprint 1 07-03-2022
Sprint Backlog 1
BACKLOG TASK & ID | STORY POINTS | STATUS | ORIGINAL ESTIMATE HOURS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a user, I want to generate PANGU format crater and boulder lists #11 | 5 | On Going | 8
Print out txt files in a PANGU list format | 1 |  | 2 | 2 | 0 | 0 | 0 | 0
keep the list inforamtion in a datat structure | 2 |  | 3 | 2 | 0 | 0 | 0 | 0
be able to print both a crater and boulder list when both have been placed | 1.5 |  | 2 | 2
include all nessisary information(size,age,depth) | 0.5 |  | 1 | 1
As a user, I want to be able to specify where on the model I want to place Boulders or craters#2 | 5 | On Going | 6
Pick a Point on a model with the mouse (x,y,z) | 2 |  | 2.5 | 2.5 | 0 | 0 | 0 | 0
Convert that x,y,z position to longitude and latatude for PANGU | 2 |  | 2.5 | 2.5 | 2 | 0 | 0 | 0
Save the point so it can be added to the lists | 1 |  | 1 | 1 | 1 | 1 | 0 | 0
As a user, I want to swap between adding boulders or craters #5 | 5 | Done | 5
Add boulder and crater modes that can be toggled between | 1.5 |  | 2 | 2 | 0 | 0 | 0 | 0
add a UI element on the designer the user can use to pick which mode they want to use | 2.5 |  | 2 | 2 | 2 | 0 | 0 | 0
save boulders and craters to different strings | 1 |  | 1 | 1 | 0 | 0 | 0 | 0
As a user, I want to be able to access the service through a web-site #8 | 2 | Done | 2
Create a html page | 1 |  | 1 | 1 | 0 | 0 | 0 | 0
locally host the page | 1 |  | 1 | 1 | 0 | 0 | 0 | 0
As a user, I want to be able to upload and work on specific asteroid models #4 | 4 | On Going | 5
find a way to accept user uploads | 2 |  | 5 | 0 | 0 | 0 | 0 | 0
check the user uploaded file is valid | 1 |  | 4 | 0 | 0 | 0 | 0 | 0
load the user uploaded model | 1 |  | 2 | 0 | 0 | 0 | 0 | 0

## Sprint 2 14-03-2022
Sprint Backlog 2
BACKLOG TASK & ID | STORY POINTS | STATUS | ORIGINAL ESTIMATE HOURS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a user, I want to generate PANGU format crater and boulder lists #11 | 5 | On Going | 8
Print out txt files in a PANGU list format | 1 |  | 2 | 2 | 0 | 0 | 0 | 0
keep the list inforamtion in a datat structure | 2 |  | 3 | 2 | 0 | 0 | 0 | 0
be able to print both a crater and boulder list when both have been placed | 1.5 |  | 2 | 2
include all nessisary information(size,age,depth) | 0.5 |  | 1 | 1
As a user, I want to be able to specify where on the model I want to place Boulders or craters#2 | 5 | On Going | 6
Pick a Point on a model with the mouse (x,y,z) | 2 |  | 2.5 | 2.5 | 0 | 0 | 0 | 0
Convert that x,y,z position to longitude and latatude for PANGU | 2 |  | 2.5 | 2.5 | 2 | 0 | 0 | 0
Save the point so it can be added to the lists | 1 |  | 1 | 1 | 1 | 1 | 0 | 0
As a user, I want to swap between adding boulders or craters #5 | 5 | Done | 5
Add boulder and crater modes that can be toggled between | 1.5 |  | 2 | 2 | 0 | 0 | 0 | 0
add a UI element on the designer the user can use to pick which mode they want to use | 2.5 |  | 2 | 2 | 2 | 0 | 0 | 0
save boulders and craters to different strings | 1 |  | 1 | 1 | 0 | 0 | 0 | 0
As a user, I want to be able to access the service through a web-site #8 | 2 | Done | 2
Create a html page | 1 |  | 1 | 1 | 0 | 0 | 0 | 0
locally host the page | 1 |  | 1 | 1 | 0 | 0 | 0 | 0